## GANTT
Task | Resources | Prior | 2024-01-20 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 |  | Comments
Purpose | Microsoft Word | 0:30
User requirements | Microsoft Word | 0:45
GANTT Chart | Microsoft Excel | 1:00 | 2:00 | 0:05 | 0:05 | 0:05 | 0:05 | 0:05 | 0:05 | 0:05 | 0:05 | 0:05 | 0:05 | 0:05 | 0:05
Pages | Microsoft Word | 0:15
Site map | Adobe Illustrator, GlooMaps | 1:00
Initial design | Google Slides | 2:00
Second & third design | Google Slides | 1:30
Design feedback | Peer | 2:00
Design feedback changes | Google Slides | 1:00
Justification | Microsoft Word | 1:30
Specification | Microsoft Word` | 2:00 | 2024-01-20: 2:30
Asset table | Microsoft Word |  | 2024-01-22: 0:15; 2024-01-24: 0:15; 2024-01-25: 0:15; 2024-01-26: 0:15; 2024-01-27: 0:15
Prepare images | Adobe Photoshop & Illustrator, Google Drawings & Slides |  | 2024-01-22: 0:15; 2024-01-24: 0:30; 2024-01-25: 0:20; 2024-01-26: 0:15
Prepare videos | YouTube, Adobe Premiere Pro |  | 2024-01-22: 0:15; 2024-01-24: 0:15; 2024-01-25: 0:20; 2024-01-26: 0:25
Create file layout | Visual Studio Code | 0:45
Create page structure | Visual Studio Code, HTML | 3:00 | 2024-01-21: 0:30
Style pages | Visual Studio Code, CSS | 3:00 | 2024-01-21: 1:00; 2024-01-22: 0:30; 2024-01-23: 0:30; 2024-01-24: 0:15; 2024-01-25: 0:30; 2024-01-26: 1:00; 2024-01-27: 0:45
Program frontend functionality | Visual Studio Code, JS | 5:00 |  | 1:30 | 0:45 | 0:45 |  | 0:40 | 1:30 | 1:00 | 1:00 | 0:30 | 0:15
Program interactive content | Visual Studio Code, JS | 1:00 |  | 1:00 | 0:45 | 0:45 |  | 0:40 | 1:30 | 1:00 | 1:00 | 0:30 | 0:15
Debug & error fix website | Visual Studio Code, Microsoft Edge DevTools | 1:00 |  | 0:30 | 0:15 | 0:15 |  | 0:15 | 0:30 | 0:15 | 0:15 | 0:30 | 0:15 | 0:15 | 0:15
Test website - UX | Google Chrome, Microsoft Edge, Mozilla Firefox, Opera GX |  | 2024-01-26: 0:30; 2024-01-27: 0:30
Website feedback | Peer |  | 2024-01-27: 2:00; 2024-01-28: 0:30
Website feedback changes | Visual Studio Code |  | 2024-01-28: 1:00; 2024-01-29: 0:30
Evaluate website | Microsoft Word |  | 2024-01-29: 0:30; 2024-01-30: 0:30; 2024-01-31: 1:00; 2024-02-01: 0:15
Improvement suggestions | Microsoft Word, GitHub Issues |  | 2024-01-30: 0:15; 2024-01-31: 0:30; 2024-02-01: 0:15
Total Time per Day (hours) |  | 27:15 | 4:30 | 4:35 | 3:05 | 2:20 | 1:20 | 3:05 | 6:00 | 5:50 | 3:50 | 2:35 | 1:35 | 1:50 | 0:50 | 68:40
|  | ↑ not just 1 day | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | ↑ + 48:00
↑ + 24:00
COLOUR KEY
Scheduled
Scheduled (Optional)
Completed
Completed with overtime
FAILED TO COMPLETE
Overtime
Note on C1: This column represents all work done Prior to finishing this GANTT chart.